## 01 Overview
MVP1 Requirements Traceability Matrix
Corrective audit: source -> specification -> machine contract -> backlog -> acceptance evidence
Verdict: PASS WITH RESIDUAL EXTERNAL RISKS. This means the specification package is coherent enough to implement; it does not mean the backend or live Manago/MCP integration has passed.
Metric | Formula/Value | Meaning
Requirements | 22 | Rows in 02 Traceability
Traceable | 22 | Requirements with a complete chain
Open/Failed | 0 | Any non-traceable requirement
Closed defects | 8 | Rows closed in 03 Defect Log
Release verdict | PASS WITH RESIDUAL EXTERNAL RISKS | MCP and backend execution evidence remain pending

## 02 Traceability
Requirements Traceability
No requirement is complete until the full chain is present
Klints · MVP1 build contract · v1.4.1 · 18 July 2026
Requirement ID | Domain | Requirement | Source | Specification | Machine Contract | Backlog | Acceptance Test | Status | Residual Risk
RQ-DCS-001 | DCS | Headline onboarding score uses exact 42 checks (28 rule + 14 drift) | DCS v1.3 catalogue | DCS v1.4.1 · 09 MVP1 Check Scope | check_definition + dcs_run | BL-002 | AT-003 | TRACEABLE | 102-check catalogue remains expansion library
RQ-DCS-002 | DCS | Failed foundation/coverage gate never produces misleading final score | DCS v1.3 Overview/Runbook | DCS v1.4.1 · 07–10 | dcs_run.schema.json | BL-004 | AT-006–007 | TRACEABLE | None
RQ-DCS-003 | DCS | All 16 pilot gating IDs are executable in MVP1 | UC v1.3 gating columns | DCS v1.4.1 · 11 Pilot Supplemental Gates | check_definition.schema.json | BL-003 | AT-004 | TRACEABLE | 12 supplemental checks are on-demand and non-headline
RQ-AF-001 | Architecture | Inventory existing assets with evidence and dependencies | Architecture v1.3 | Architecture v1.4.1 · 02/05 | architecture_asset.schema.json | BL-008 | AT-011 | TRACEABLE | MCP depth remains external
RQ-AF-002 | Architecture | No retire/consolidate verdict without dependency proof | Architecture v1.3 Overview | Architecture v1.4.1 · 05/06 | architecture_verdict.schema.json | BL-008–009 | AT-011 | TRACEABLE | None
RQ-UC-001 | Use cases | Exact 16 pilot build scope with detailed workflow logic | UC v1.3 catalogue/blueprints | UC v1.4.1 · 07/08 | workflow_blueprint.schema.json + 16 JSON files | BL-010/016 | AT-002/017–018 | TRACEABLE | None
RQ-UC-002 | Use cases | UC-06B remains a variant of canonical UC-06 | UC v1.3 UC-06 | UC v1.4.1 · 07 MVP1 Pilot Scope | parent_use_case_id in workflow schema | BL-010 | AT-017 | TRACEABLE | None
RQ-ORCH-001 | Orchestration | Priority uses canonical v1.3 four-factor 0–3 formula | Orchestration v1.3 · 02 | Orchestration v1.4.1 · 02/08/09 | orchestration_task.schema.json | BL-011 | AT-012 | TRACEABLE | Former conflicting 0–100 formula removed
RQ-ORCH-002 | Orchestration | Dependencies, cycles and waves are deterministic | Orchestration v1.3 · 03/04 | Orchestration v1.4.1 · 07/09 | orchestration_task.schema.json | BL-012 | AT-013–014 | TRACEABLE | Same-wave order uses topological sequence
RQ-REPORT-001 | Reporting | Downloadable governance-grade Assessment Report is an explicit task | Orchestration v1.3 · 01/06 | Orchestration v1.4.1 · 07–10 | assessment_report + orchestration_task | BL-013 | AT-020–022 | TRACEABLE | None
RQ-REPORT-002 | Reporting | Free report shows full diagnostic and locks remediation | Orchestration v1.3 · 06 A6:D18 | Orchestration v1.4.1 · 06/10 | assessment_report.schema.json | BL-013 | AT-021 | TRACEABLE | None
RQ-REPORT-003 | Reporting | PDF, JSON and in-app variants share one governed payload | Orchestration v1.3 · 06 row 18 | Orchestration v1.4.1 · 10 | assessment_report + OpenAPI | BL-014 | AT-023 | TRACEABLE | None
RQ-REPORT-004 | Reporting | Report API supports create/status/download with idempotency | Derived implementation requirement | Orchestration v1.4.1 · 10 | assessment_report_api.openapi.json | BL-014 | AT-020/026–027 | TRACEABLE | Regenerate semantics documented in workbook
RQ-REPORT-005 | Reporting | No cross-tenant report metadata or bytes | Neutral data-layer boundary | Orchestration v1.4.1 · 10 | assessment_report.schema.json + OpenAPI | BL-015 | AT-024/027 | TRACEABLE | Backend evidence not yet run
RQ-REPORT-006 | Reporting | Default report excludes contact-level PII | Governance requirement | Orchestration v1.4.1 · 10 | assessment_report.schema.json | BL-015 | AT-025 | TRACEABLE | Backend scan not yet run
RQ-REPORT-007 | Reporting | Incomplete inputs yield explicit INCOMPLETE report with null score | DCS no-incomplete-score rule | Orchestration v1.4.1 · 09/10 | assessment_report.schema.json | BL-013 | AT-022 | TRACEABLE | None
RQ-CAP-001 | Capabilities | MCP is discovery-required until evidence exists | User amendment + new Manago MCP | Capability Matrix v1.1 | capability_record.schema.json | BL-006–007 | AT-008–010 | TRACEABLE | External verification remains pending
RQ-CAP-002 | Capabilities | Every core pilot has confirmed or human fallback | Manago capabilities/agent docs | Capability Matrix v1.1 · 05 | workflow blueprint capability_dependencies | BL-006/016 | AT-008 | TRACEABLE | MCP write path remains external
RQ-SAFE-001 | Safety | Side effects require scoped approval and idempotency | Orchestration v1.3 · 05 | Orchestration v1.4.1 · 08/09 | approval_token + orchestration_task | BL-017 | AT-015–016 | TRACEABLE | None
RQ-QA-001 | QA | Specification validation must not be reported as backend PASS | Corrective audit finding | Acceptance Matrix v1.2 | qa_result.schema.json | BL-018 | AT-001–030 | TRACEABLE | Backend remains NOT_RUN
RQ-HANDOFF-001 | Handoff | Signed handoff references QA, approval, artifacts and manifest hash | Orchestration v1.3 Wave 6 | Orchestration v1.4.1 · 07/09 | handoff_package.schema.json | BL-020–021 | AT-028 | TRACEABLE | Backend not run
RQ-PACK-001 | Package | Every release requirement maps to a spec, contract, backlog and test | Corrective audit commitment | Requirements Traceability Matrix | manifest + QA report | BL-021 | AT-030 | TRACEABLE | External MCP is explicitly residual

## 03 Defect Log
Corrective Defect Log
Defects found during the traceability audit; closure requires changed artifact plus regression test
Klints · MVP1 build contract · v1.4.1 · 18 July 2026
Defect ID | Severity | Finding | Root Cause | Correction | Regression Test | Changed Artifacts | Status
DEF-001 | P0 | Downloadable PDF requirement existed only as product text, not an executable task/contract | Traceability stopped at workbook presence | Added REPORT/EXPORT tasks, report sheet, schema, OpenAPI, backlog, fixtures and tests | AT-020–027 | Orchestration, schemas, backlog, tests, Blueprint, README | CLOSED
DEF-002 | P0 | v1.4 contained a priority formula conflicting with v1.3 | New algorithm invented a second normalized model | Restored canonical four-factor 0–3 formula end to end | AT-012 | Orchestration, task schema, Blueprint | CLOSED
DEF-003 | P0 | Acceptance matrix used PASS before backend execution | Specification and implementation evidence were conflated | Split Specification Status from Backend Status; all backend tests start NOT_RUN | AT-001–030 | Acceptance Matrix, QA report, Blueprint | CLOSED
DEF-004 | P0 | 12 gating Check IDs used by pilots were outside exact 42 scope | Headline score scope was treated as complete executable gate registry | Added explicit on-demand supplemental gate registry without changing headline score | AT-004 | DCS workbook, backlog, README, manifest | CLOSED
DEF-005 | P1 | Lumera task rows 2–6 were blank in exported workbook | Legacy merged cells overlapped the new table | Unmerged cells and rebuilt full worked example including reports | AT-014/028 | Orchestration workbook | CLOSED
DEF-006 | P1 | Wave formula forced every dependency into a later wave and could overflow 0–6 | Dependency order and stage floor were conflated | Use type floor plus topological ordering within the same wave | AT-014 | Orchestration workbook, Blueprint | CLOSED
DEF-007 | P1 | Blueprint data_contract.required_fields contained Check IDs, not fields | Generator reused the gating array | Replaced with use-case-specific canonical field names | AT-002 | 16 blueprint JSON files | CLOSED
DEF-008 | P1 | Referenced runtime objects lacked machine schemas (DCS run, capability, approval, QA, handoff) | Original contract set covered only seven objects | Added six missing schemas; total is now 13 | AT-001 | Machine Contracts, Blueprint, README | CLOSED