## 01 Acceptance Tests
MVP1 Acceptance Test Matrix
Specification evidence is separated from backend execution status
VALIDATED means the contract/fixture is internally present and coherent. It does not mean Rohan's backend test has run. Backend Status remains NOT_RUN until implementation evidence exists.
Test ID | Domain | Test | Fixture/Source | Specification Status | Backend Status | Priority | Method | Pass Criteria | Owner | External Dependency
AT-001 | Contracts | All 13 schemas parse and expose version | Schema files | VALIDATED | NOT_RUN | P0 | Automated | 0 schema errors | Rohan | —
AT-002 | Contracts | All 16 blueprints validate | Blueprint files | VALIDATED | NOT_RUN | P0 | Automated | 0 validation errors; 16 unique IDs | Rohan | —
AT-003 | DCS | Headline scope count and classes | 11/09 scope sheets | VALIDATED | NOT_RUN | P0 | Automated | 28 rule + 14 drift = 42 | Rohan | —
AT-004 | DCS | All pilot gates resolve to headline or supplemental registry | Pilot blueprints + 11 Pilot Supplemental Gates | VALIDATED | NOT_RUN | P0 | Automated | 0 unresolved gate IDs; supplemental count=12 | Rohan | —
AT-005 | DCS | Lumera score matches golden fixture | Scoring fixture | VALIDATED | NOT_RUN | P0 | Automated | Exact to 4 decimals; state exact | Rohan | —
AT-006 | DCS | Gate fail suppresses score | gate_fail.json | VALIDATED | NOT_RUN | P0 | Automated | State BLOCKED; headline null | Rohan | —
AT-007 | DCS | Partial sweep never emits final score | partial_sweep.json | VALIDATED | NOT_RUN | P0 | Automated | State INCOMPLETE | Rohan | —
AT-008 | Capabilities | Unverified MCP cannot execute without fallback | Capability matrix | VALIDATED | NOT_RUN | P0 | Automated | Resolver returns fallback or BLOCKED | Rohan | —
AT-009 | MCP | Read discovery and isolation evidence complete | MCP-D-01–11,15 | PENDING_EXTERNAL | BLOCKED_EXTERNAL | P0 | Integration | Every test PASS/FAIL with evidence | Rohan + Manago | Tenant access
AT-010 | MCP | Write tests are draft-only and reversible | MCP-D-12–14 | PENDING_EXTERNAL | BLOCKED_EXTERNAL | P0 | Integration | No production activation; rollback proven | Rohan + Manago | External approval
AT-011 | Architecture | No Retire/Consolidate without dependency proof | Dependency fixture | VALIDATED | NOT_RUN | P0 | Automated | Verdict becomes INCOMPLETE/KEEP | Rohan | —
AT-012 | Orchestration | Canonical priority formula reproduces v1.3 examples | Priority fixture | VALIDATED | NOT_RUN | P0 | Automated | CC-07=2.20; LE-09=2.90; UC-23 case=1.40 | Rohan | —
AT-013 | Orchestration | Dependency cycle blocked | dependency_cycle.json | VALIDATED | NOT_RUN | P0 | Automated | Exact cycle path emitted | Rohan | —
AT-014 | Orchestration | Wave order respects prerequisites without false overflow | Lumera tasks | VALIDATED | NOT_RUN | P0 | Automated | 0–6 only; no task before dependency | Rohan | —
AT-015 | Safety | No side effect without approval token | Approval schema + write fixture | VALIDATED | NOT_RUN | P0 | Automated | State AWAITING_APPROVAL | Rohan | —
AT-016 | Safety | Idempotent replay | Task/report fixture | VALIDATED | NOT_RUN | P0 | Automated | Same result; no duplicate write/artifact | Rohan | —
AT-017 | Workflow | UC-06B parent mapping, holdout, consent and global exit | UC-06B blueprint | VALIDATED | NOT_RUN | P0 | Automated | parent=UC-06; all guards present | Rohan | —
AT-018 | Workflow | Namespace separation | All blueprints | VALIDATED | NOT_RUN | P0 | Automated | Details klints_; tags klints: | Rohan | —
AT-019 | QA | Hard-fail domain blocks staging despite score >=80 | QA fixture | VALIDATED | NOT_RUN | P0 | Automated | Staging denied | Rohan | —
AT-020 | Reporting | Report schema and OpenAPI parse | Report contracts | VALIDATED | NOT_RUN | P0 | Automated | 0 validation/parser errors | Rohan | —
AT-021 | Reporting | Free report contains full diagnostic and locks remediation | Free report fixture | VALIDATED | NOT_RUN | P0 | Automated | Required sections present; remediation null/locked | Rohan | —
AT-022 | Reporting | Incomplete report never exposes headline score | Incomplete report fixture | VALIDATED | NOT_RUN | P0 | Automated | status/state INCOMPLETE; score null; gaps prominent | Rohan | —
AT-023 | Reporting | PDF and JSON use identical payload/version hashes | Render fixture | VALIDATED | NOT_RUN | P0 | Automated | payload_hash and lineage match | Rohan | —
AT-024 | Reporting | Cross-tenant metadata/download denied without leakage | API negative fixture | VALIDATED | NOT_RUN | P0 | Security | 404/403; no metadata or bytes | Rohan | —
AT-025 | Reporting | Report payload contains no contact-level PII | Report payload scan | VALIDATED | NOT_RUN | P0 | Automated | No email/phone/contact ID/raw event rows | Rohan | —
AT-026 | Reporting | Report generation and retry are idempotent | Failure/retry fixture | VALIDATED | NOT_RUN | P0 | Automated | Same key+payload returns one artifact set | Rohan | —
AT-027 | Reporting | Expired or unauthorized download blocked and audited | API security fixture | VALIDATED | NOT_RUN | P0 | Security | 410/404/403 and audit event | Rohan | —
AT-028 | E2E | Lumera package emits diagnostic report, final report and handoff | Full fixtures | VALIDATED | NOT_RUN | P0 | Automated | All artifact IDs, hashes and dependencies exact | Rohan | —
AT-029 | Pack QA | All workbooks legible and formula-error free | 9 workbooks | VALIDATED | N/A | P1 | Manual/Automated | All sheets rendered; no error tokens | Klints | —
AT-030 | Traceability | Every release requirement maps to spec, contract, backlog and test | Traceability Matrix | VALIDATED | N/A | P0 | Automated/Review | 0 unresolved P0 requirements | Klints | —

## 02 Release Gates
Release Gates
Documentation readiness and backend release readiness are separate gates
Klints · MVP1 build contract · v1.4.1 · 18 July 2026
Gate | Required State | Blocking Tests | Specification Pack | Backend | Next Owner
G1 Contract completeness | VALIDATED | AT-001–004 | VALIDATED | NOT_RUN | Rohan
G2 Deterministic scoring | PASS | AT-005–007 | VALIDATED | NOT_RUN | Rohan
G3 Capability truth | External evidence recorded | AT-008–010 | PENDING_EXTERNAL for MCP | BLOCKED_EXTERNAL | Rohan + Manago
G4 Architecture/orchestration safety | PASS | AT-011–019 | VALIDATED | NOT_RUN | Rohan
G5 Report composition/export/security | PASS | AT-020–027 | VALIDATED | NOT_RUN | Rohan
G6 E2E and traceability | PASS | AT-028–030 | VALIDATED | NOT_RUN/N/A | Rohan + Klints