## 01 Backlog
Rohan Implementation Backlog
Build-order backlog derived from the corrected v1.4.1 specifications
Klints · MVP1 build contract · v1.4.1 · 18 July 2026
ID | Priority | Area | Deliverable | Depends On | Acceptance | Owner | Status | Effort pts | Milestone | External
BL-001 | P0 | Contracts | Implement 13 JSON Schema contracts + version registry | — | All schemas parse; invalid fixtures rejected | Rohan | READY | 5 | MVP1-A | No
BL-002 | P0 | DCS | Implement exact 42-check headline score registry | BL-001 | 28 RULE_BASED + 14 DRIFT; IDs exact | Rohan | READY | 5 | MVP1-A | No
BL-003 | P0 | DCS | Implement 12 on-demand pilot supplemental gates | BL-001, BL-002 | Every pilot gate resolves; supplemental FAIL blocks dependent pilot only | Rohan | READY | 5 | MVP1-A | No
BL-004 | P0 | DCS | Implement scoring/gate/coverage/confidence engine | BL-002 | Golden dataset matches; incomplete sweep has no score | Rohan | READY | 5 | MVP1-A | No
BL-005 | P0 | Connectors | Implement checkpointed Manago/Shopify/ERP reads | BL-001 | No score from partial sweep | Rohan | READY | 8 | MVP1-A | No
BL-006 | P0 | Capabilities | Persist capability records and deterministic resolver | BL-001 | Discovery, required-build and fallback states enforced | Rohan | READY | 5 | MVP1-A | No
BL-007 | P0 | MCP | Run read-only MCP discovery tests 01–11 and isolation test 15 | BL-006 | Evidence stored per test | Rohan + Manago | BLOCKED_EXTERNAL | 5 | MVP1-A | Yes
BL-008 | P0 | Architecture | Implement asset + dependency graph | BL-001, BL-005 | No destructive verdict without graph evidence | Rohan | READY | 8 | MVP1-B | No
BL-009 | P0 | Architecture | Implement per-asset and architecture verdicts | BL-008, BL-004 | Golden verdict fixture passes | Rohan | READY | 5 | MVP1-B | No
BL-010 | P0 | Use cases | Load exact 16 pilot registry; preserve UC-06 parent/UC-06B variant | BL-001, BL-003 | Count=16; IDs unique; all gates resolvable | Rohan | READY | 3 | MVP1-B | No
BL-011 | P0 | Orchestration | Implement canonical four-factor priority formula (0–3) | BL-001 | Source examples reproduce exactly; no 0–100 alternative | Rohan | READY | 5 | MVP1-B | No
BL-012 | P0 | Orchestration | Implement DAG validation, cycle detection and 0–6 wave floors | BL-011 | Stable order; same-wave dependencies do not overflow | Rohan | READY | 8 | MVP1-B | No
BL-013 | P0 | Reporting | Implement report composition and free/paid/living gating | BL-001, BL-004, BL-009 | Payload validates; locked sections exact | Rohan | READY | 8 | MVP1-B | No
BL-014 | P0 | Reporting | Implement PDF/JSON render, versioning, hashing, storage and download API | BL-013 | Artifacts share payload hash; API contract passes | Rohan | READY | 8 | MVP1-C | No
BL-015 | P0 | Reporting | Implement tenant isolation, PII minimization, retention and audit | BL-014 | Cross-tenant and PII tests block without leakage | Rohan | READY | 5 | MVP1-C | No
BL-016 | P0 | Build guides | Generate Manago build package from blueprint JSON | BL-010, BL-006 | MCP route or human fallback resolved | Rohan | READY | 8 | MVP1-C | No
BL-017 | P0 | Approvals | Implement diff-bound approval tokens and audit events | BL-011 | No side effect without valid token | Rohan | READY | 8 | MVP1-C | No
BL-018 | P0 | QA | Implement QA >=80 plus hard-fail domains | BL-016 | Hard test fail blocks staging | Rohan | READY | 8 | MVP1-C | No
BL-019 | P1 | MCP | Run sandbox write/rollback tests 12–14 | BL-007, BL-017 | Draft only; rollback proof captured | Rohan + Manago | BLOCKED_EXTERNAL | 5 | MVP1-C | Yes
BL-020 | P0 | E2E | Pass Lumera E2E through diagnostic PDF/JSON and final handoff | BL-004, BL-009, BL-012, BL-015, BL-018 | Expected score, tasks, reports, waves and handoff exact | Rohan | READY | 8 | MVP1-C | No
BL-021 | P1 | Release | Emit signed manifest, versions, hashes, traceability and audit bundle | BL-020 | Pack reproducible and immutable | Rohan | READY | 3 | MVP1-C | No

## 02 Milestones
Milestones
Suggested implementation sequence; scope, not calendar commitment
Klints · MVP1 build contract · v1.4.1 · 18 July 2026
Milestone | Exit Outcome | Backlog IDs | Hard Gate | Demo | Owner
MVP1-A Contracts & scoring | 13 schemas, connectors, resolver, 42 headline + 12 preflight checks | BL-001–BL-007 | Golden scoring and gate-resolution tests | DCS with evidence/coverage | Rohan
MVP1-B Architecture, plan & report payload | Dependency graph, verdicts, pilot registry, orchestrator, report composition | BL-008–BL-013 | Cycle/verdict/report-payload fixtures pass | Prioritized waves + diagnostic payload | Rohan
MVP1-C Build, render, QA & handoff | PDF/JSON API, security, build guides, approvals, QA, Lumera E2E | BL-014–BL-021 | E2E acceptance matrix passes | Downloadable report + signed handoff | Rohan + Klints