## 00_How_to_read
Klints — Client Blockers & Gaps Brief
Date | 2026-09-23
Tenant example | yoyo (local demo)
Latest DCS | Run 526 snapshot still illustrative · writebacks LE-01/05/09, SP-07, PT-04 now Live OK (WB-08..WB-13); re-score after Approve to clear
Latest AF | INCOMPLETE · evidence_coverage 0.42 · 14/16 lifecycle gaps · 0 workflows
Colour key
FALSE / Demo / Expected | Looks like a blocker in UI but is expected, environmental, or not a Klints product defect
TRUE / Product gap | Real missing product capability or unfinished wiring (e.g. writeback not connected)
Live OK | Working path today
Demo trap | Gate blocks journey while Fix path cannot clear the same check
Sheets in this workbook
01_Exec_Summary | One-page client summary
02_Architecture_AF | Why AF shows INCOMPLETE — false vs true
03_AF_Probe_Detail | Per-probe status and client wording
04_Writeback_Gaps | Checks labeled Automated writeback vs actually executable
05_Pilot_Handoff_Traps | Studio / QA / Handoff blockers and demo flags
06_Open_DCS_Fails | Current FAIL/WARN on latest score (yoyo)
07_Recommended_Actions | What to build vs what to explain vs demo bypass

## 01_Exec_Summary
Theme | What client sees | Classification | Plain-language explanation | Client impact
Architecture Assessment | Mode = INCOMPLETE · graph incomplete · ~14 lifecycle gaps | FALSE / Demo / Expected | AF ran successfully. Manago returned 0 workflows and there is no segment list API, so coverage stays ~42% (gate needs 80%). Engine behaviour is correct — not a broken Architecture module. | Looks like Architecture is broken; it is incomplete because inventory is empty, not because Klints failed to run.
PT-04 on Fix + Handoff | PT-04 was FAIL on Fix; Handoff demo may still open while QA FAIL | Closed for writeback (WB-11+WB-12) · Demo trap residual | PT-04 money truth now has Fix Approve: stamps klints_net_ltv; re-run DCS PASSes when stamp ≈ Shopify net (WB-11+WB-12). Demo REQUIRE_HANDOFF_QA_PASS=False still opens Handoff while QA FAIL — bypass ≠ writeback. | Client can clear PT-04 via Fix→Approve→re-score. Demo may still show Handoff open with FAIL for story.
Writeback for many DCS checks | Some checks still say Automated writeback but Approve disabled | TRUE / Product gap (shrinking) | Live OK now: CI-01, CC-03, WB-SHOP-01, LE-01 (WB-08), SP-07 (WB-09), LE-09 (WB-10), PT-04 (WB-11+12), LE-05 (WB-13). Still open/stub: CI-03, SP-01, LE-02, CI-05, PT-01/03, SP-03, CC-01/02, BR-01, LE-08; LE-04 intentional OFF. | Highest-pain gates LE-01/05/09/PT-04/SP-07 are executable; remaining catalogue promises still need mappings.
Studio Generate (demo) | Was blocked by AF INCOMPLETE + gating FAILs | Demo / expected (mitigated) | Demo env flags REQUIRE_ARCHITECTURE_PILOT_GATES=False and REQUIRE_PILOT_GATING_CHECKS=False unlock Studio without changing AF/DCS truth tiles. REQUIRE_HANDOFF_QA_PASS=False separately opens Handoff while QA FAIL. | Demo can show Fix→Studio while AF/PT-04 stay FAIL for story; production should keep flags True.
DCS headline ~77 | Score improved after data fixes + PT-01 join fix | Mixed | SP-03/LE-09 style Manago data fixes + PT-01 join fix (code). PT-04 can now clear via writeback (WB-11+12) instead of staying FAIL forever. | Headline can be high; Fix can clear PT-04 when company writebacks enabled.
MCP / Handoff Send | Full MCP auto-send not the live Handoff path | Product / roadmap | HO-02 is human activation (approve→guide→confirm), not MCP auto-send. MCP helps Manago writes when connected; Handoff ≠ writeback. | Do not equate Handoff unlock with Manago write.

## 02_Architecture_AF
ID | Symptom (UI) | Classification | Why it looks bad | Why it is FALSE or TRUE | What would make it real AUGMENT | Evidence / source
AF-01 | Architecture mode INCOMPLETE | FALSE / Demo / Expected | Client reads Incomplete as failure | Job status=succeeded. Mode gate: evidence_coverage 0.42 < 0.80. No critical_defects. Correct PRD decision order. | Manago workflows list >0 + richer segment where-used so coverage ≥0.80 | verdicts.py rollup_mode; AF assessment ccbebffe…
AF-02 | graph_complete = False / 0 edges | FALSE / Demo / Expected | Looks like graph builder broken | Documented: without workflow inventory + segment where-used, graph stays partial so Retire/Consolidate cannot fire. Expected. | Workflow definitions + segment dependency graph from Manago | architecture/graph.py note on MCP/segment
AF-03 | 14 of 16 lifecycle stages gap | FALSE / Demo / Expected | Looks like Klints cannot map lifecycle | Only 3 PROPERTY assets found (ORDER_AVG, ORDER_NUMBER, ORDER_SUMMARY) → stages 4–5 only. No workflow assets to cover other stages. Accurate for empty automation estate. | Create/list Manago automations covering stages; re-run AF | WF-12 probe; lifecycle_model 16 stages
AF-04 | WF-01 succeeded but 0 workflows | FALSE / Demo / Expected (platform data) | Probe green but inventory empty | API/connector path ran; Manago returned empty workflow list (or account has no automations). Not an AF crash. | Configure workflows in Manago (or fix API permissions) then re-import | inventory WF-01
AF-05 | WF-04 / WF-09 / TAG-04 incomplete | FALSE / Demo / Expected | Multiple incomplete probes | Downstream of 0 workflows / no TAG assets / no segment list API. Structural, not random failures. | Same as AF-02/AF-04 | probe_coverage on latest AF
AF-06 | weighted_score = blank | Not a defect | Looks unscored | Score intentionally not computed when coverage gate fails. Correct. | Pass coverage gate first | verdicts.py
AF-07 | Studio blocked by Architecture | Demo trap (mitigated) | Cannot Generate while AF Incomplete | By design when REQUIRE_ARCHITECTURE_PILOT_GATES=True. Demo may set False — AF tile unchanged. | Real AUGMENT or keep demo bypass documented | .env REQUIRE_ARCHITECTURE_PILOT_GATES
AF-08 | 7 DCS impaired checks on WF-05 | TRUE / Product gap (data quality) | Architecture surfaces DCS pain | Real open DCS FAILs on tenant (see sheet 06). With 0 workflows, FIX_FIRST attach is empty — still true data issues. | Clear DCS FAILs (esp. writeback-capable ones) + workflows | WF-05 + DCS run 526

## 03_AF_Probe_Detail
Probe | Status | Classification | Client wording | Technical note
WF-01 | succeeded | FALSE / Demo / Expected | Workflow inventory call OK — estate empty | 0 workflows returned
WF-04 | incomplete | FALSE / Demo / Expected | Cannot map triggers — no workflows | no_workflows
WF-09 | incomplete | FALSE / Demo / Expected | Dependency graph incomplete — no segment list + no workflows | Expected partial graph
TAG-01 | partial | FALSE / Demo / Expected | Tag inventory limited | 0 tags / segment list deferred
TAG-04 | incomplete | FALSE / Demo / Expected | No tag assets to analyse | Downstream of empty inventory
PROP-01 | partial | FALSE / Demo / Expected | Only a few properties inferred from contacts | 3 properties from snapshot
PROP-04 | succeeded | OK | Property orphan check ran | Expected with 0 workflow edges
WF-05 | succeeded | TRUE / Product gap (data) | DCS join ran — open consistency issues remain | 7 impaired checks, 0 FIX_FIRST assets
WF-06 | partial | FALSE / Demo / Expected | No consent FAIL cluster in this score slice | Normal if CC-* not failing
WF-07 | succeeded | OK | No overlap clusters (no workflows) | Expected
WF-03 | succeeded | FALSE / Demo / Expected | Retire blocked by incomplete graph | By design until graph_complete
WF-10 | partial | FALSE / Demo / Expected | Measurement check not in FAIL set | ME-02 often UNKNOWN without workflows
WF-12 | partial | FALSE / Demo / Expected | Lifecycle coverage thin — only 2/16 stages | Only ORDER_* properties mapped

## 04_Writeback_Gaps
check_id | CheckMaster says | Mapping file | Registry enabled | DB allowlisted | Classification | Client wording | Blocks Handoff/pilots?
CI-01 | Automated writeback | Yes | Yes | Yes | Live OK | Fix → Approve → execute works (sandbox rules) | If FAIL, yes until PASS
CC-03 | Automated writeback + Manual | Yes | Yes | Yes | Live OK | Fix → Approve → execute works (sandbox rules) | If FAIL, yes until PASS
WB-SHOP-01 | Sandbox proof | Yes | Yes | Yes | Live OK | Shopify note sandbox proof | N/A (not catalogue gate)
CI-03 | Automated writeback | Stub | No | No | TRUE / Product gap | Shown as writeback-class; cannot execute | If FAIL / used as gate
LE-01 | Automated writeback | Yes | Yes | Yes | Live OK | Fix → Approve → PURCHASE event_ingest (WB-08); sandbox max_rows default 10 | If FAIL, yes until PASS / re-score
LE-04 | Integration + Manual (not pure WB) | Stub | No | No | FALSE / Demo / Expected (intentional off) | PRD: keep Approve OFF | UC-23 etc.
SP-01 | Stub mapping | Stub | No | No | TRUE / Product gap | Tag consolidation stub | If gated
PT-04 | Automated writeback | Yes | Yes | Yes | Live OK | Stamps klints_net_ltv (WB-11); re-score PASSes when stamp ≈ Shopify net (WB-12). Prefer LE-09 PASS first. | Can clear via Approve→re-score; demo Handoff may still open while FAIL if REQUIRE_HANDOFF_QA_PASS=False
LE-09 | Integration + Automated writeback | Yes | Yes | Yes | Live OK | RETURN event_ingest from shopify_only_return (WB-10); EVENT.INGEST batch ceiling | Related to PT-04; clear via Approve→re-score
LE-02 | Automated writeback | NONE | — | No | TRUE / Product gap | Not execute-ready | If FAIL
LE-05 | Automated writeback | Yes | Yes | Yes | Live OK | Order-level PURCHASE gap event_ingest (WB-13); prefer Fix LE-05 over dual LE-01 Approve | UC-06B gate — clear via Approve→re-score
CI-05 | Automated writeback | NONE | — | No | TRUE / Product gap | Link key — not execute-ready | If FAIL
PT-01 | Integration + Automated writeback | NONE | — | No | TRUE / Product gap (partially mitigated) | Catalog resolve; join fix in Klints may PASS without Manago write | Several UCs
PT-03 | Integration + Automated writeback | NONE | — | No | TRUE / Product gap | Needs Manago catalog ingest often UNKNOWN | If gated
SP-03 | Automated writeback | NONE | — | No | TRUE / Product gap | Property format — ops/script historically | If FAIL
SP-07 | Automated writeback | Yes | Yes | Yes | Live OK | Namespace collision rename (WB-09); re-run DCS after Approve | UC-23 — clear via Approve→re-score
CC-01 | Integration + Automated writeback | NONE | — | No | TRUE / Product gap | Not execute-ready | UC-06B
CC-02 | Integration + Automated writeback | NONE | — | No | TRUE / Product gap | Not execute-ready | UC-06B
BR-01 | Automated writeback | NONE | — | No | TRUE / Product gap | ERP margin — often NOT_CONNECTED without ERP | If gated
LE-08 | Integration + Automated writeback | NONE | — | No | TRUE / Product gap | Not execute-ready | If FAIL

## 05_Pilot_Handoff_Traps
ID | Stage | Blocker | Classification | Client wording | Mitigation today
T1 | Opportunities / Studio | AF mode INCOMPLETE blocks Generate | Demo trap (mitigated) | Architecture looks broken so Studio locked | REQUIRE_ARCHITECTURE_PILOT_GATES=False (demo only); AF tile stays INCOMPLETE
T2 | Opportunities / Studio | Gating check FAIL (e.g. PT-04) blocks Generate | Demo trap (mitigated) | Need pilots while keeping FAIL on Fix for story | REQUIRE_PILOT_GATING_CHECKS=False (demo only); DCS tiles unchanged
T3 | Fix | PT-04 FAIL visible | OK for story | Issue exists for Fix narrative | Keep FAIL until intentional clear
T4 | Fix → Approve writeback | PT-04 was missing mapping; now Live OK (WB-11+12) | Closed (writeback shipped) | Fix → Approve stamps klints_net_ltv; re-run DCS to PASS | Enable company writebacks; Approve → re-score. Demo may still keep FAIL for story.
T5 | QA → Handoff | Was: Handoff locked while PT-04 / package QA FAIL | Demo trap (mitigated) + by design in prod | Looks like Handoff is required to fix PT-04 — incorrect. Handoff waits for QA PASS in production; writeback applies the fix. Demo opens Handoff without clearing PT-04. | REQUIRE_HANDOFF_QA_PASS=False (demo only). Or clear PT-04 via Fix Approve (WB-11+12) then QA PASS.
T6 | Handoff vs Manago live | Confusion: Handoff = live write | FALSE understanding | Handoff ≠ Manago write. Writeback/MCP/script writes live; Handoff is package readiness. | Client education (this workbook)
T7 | Writeback global | WRITEBACKS_ENABLED default False; company opt-in | Product / config | Execute may be off even for CI-01/CC-03 | Enable per company sandbox rules per WB-02/03
T8 | QA → Handoff (demo flag) | Package QA FAIL blocked Handoff CTA / stage | Demo / expected (mitigated) | Need Handoff page for Fix story while PT-04 / package QA stay FAIL | REQUIRE_HANDOFF_QA_PASS=False — FE+BE stage/approve honor flag; still need a QA run row. Default True in production.

## 06_Open_DCS_Fails
check_id | Status | Summary (latest yoyo run 526) | Writeback executable? | Notes for client
CI-01 | FAIL | Manago vs Shopify contact universe delta (manago_only / relative delta high) | Yes (Live OK) | Can use Fix Approve path when company/sandbox gates allow
CI-03 | FAIL | High Manago duplicate rate / clusters | No (stub) | Needs CI-03 merge writeback or manual merge
CI-05 | FAIL | Link key reused / integrity | No mapping | Identity link hygiene — not execute-ready
CI-13 | WARN | Elevated dead-state share | No | Warning — monitor
LE-11 | FAIL | Event ingestion loss / drop-risk events | No mapping | Lifecycle ingest quality
LE-13 | FAIL | Event volume drift | No mapping | Often volatile; careful to force
PT-04 | FAIL | Net vs Manago lifetime: refund_blind / overstatement | Yes (Live OK — WB-11+12) | Can clear via Fix Approve (klints_net_ltv stamp) then re-score; demo may keep FAIL for Fix story

## 07_Recommended_Actions
Priority | Action | Type | Owner suggestion | Outcome for client
P0 | Document AF INCOMPLETE as expected without Manago workflows/segment graph — not a Klints AF defect | Explain | CS / Solutions | Removes false Architecture scare
P0 | PT-04 writeback shipped (WB-11+12). Demo policy still: REQUIRE_HANDOFF_QA_PASS=False opens Handoff while QA/PT-04 FAIL. Prefer Approve→re-score to clear for real pilots. | Done (WB) · Demo policy residual | Product + Eng (done) / Demo eng | Real Fix clear available; demo trap documented separately
P1 | Next writeback mappings for remaining pain: LE-02, CI-03, CC-01/02, CI-05 (LE-01/05/09, SP-07, PT-04 already Live) | Build | Eng (WB track) | Fix→Approve matches remaining CheckMaster promises
P1 | Enable stubs CI-03 / SP-01 only when transforms + capability status CONFIRMED (LE-01 already Live WB-08) | Build | Eng | Avoid half-enabled Approve
P2 | Keep demo flags documented: REQUIRE_ARCHITECTURE_PILOT_GATES / REQUIRE_PILOT_GATING_CHECKS / REQUIRE_HANDOFF_QA_PASS — False demo only (defaults True in prod) | Ops | Demo eng | Studio + Handoff walkthrough unlocked without lying on DCS/AF/QA score tiles
P2 | For live Manago estate demos: create sample workflows so AF can leave INCOMPLETE | Data / Manago | Client or CS | True AUGMENT story
P3 | Client FAQ: Handoff ≠ writeback; MCP/writeback = live Manago; Handoff = readiness after QA | Explain | CS | Stops process confusion